## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Candidate registration with name, email and password | MUST HAVE | No Dependency | Project Team | 3- Completed
S1 | S1 | US-002 | Capture and store candidate registration photograph using OpenCV | MUST HAVE | US-001 | Project Team | 3- Completed
S1 | S1 | US-003 | Secure candidate login with password hashing and session creation | MUST HAVE | US-001 | Project Team | 3- Completed
S2 | S2 | US-004 | Provide candidate dashboard with current and previous examination sessions | MUST HAVE | US-003 | Project Team | 3- Completed
S2 | S2 | US-005 | Verify candidate identity before starting the examination | MUST HAVE | US-002, US-003 | Project Team | 3- Completed
S2 | S2 | US-006 | Create exam session and maintain exam lifecycle status | MUST HAVE | US-003 | Project Team | 3- Completed
S3 | S3 | US-007 | Display randomized multiple-choice questions and save candidate answers | MUST HAVE | US-006 | Project Team | 3- Completed
S3 | S3 | US-008 | Monitor browser events such as tab switching and focus loss | MUST HAVE | US-007 | Project Team | 3- Completed
S3 | S3 | US-009 | Monitor webcam frames for face, multiple-face and eye-detection events | MUST HAVE | US-007 | Project Team | 3- Completed
S4 | S4 | US-010 | Apply rule-based thresholds to generate integrity violations | MUST HAVE | US-008, US-009 | Project Team | 3- Completed
S4 | S4 | US-011 | Generate integrity score, risk information and monitoring report | SHOULD HAVE | US-010 | Project Team | 3- Completed
S4 | S4 | US-012 | Cluster completed sessions using K-Means behaviour analytics | SHOULD HAVE | US-010 | Project Team | 3- Completed
S5 | S5 | US-013 | Validate registration, authentication, monitoring and session completion flows | MUST HAVE | US-001 to US-012 | Project Team | 3- Completed
S5 | S5 | US-014 | Prepare project evidence, defect records and final submission documentation | MUST HAVE | US-013 | Project Team | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-001 | 1 | Create candidate registration form and validation | Sprint 1 | Sprint 1 | Project Team | Design | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Implement candidate model and database persistence | Sprint 1 | Sprint 1 | Project Team | Coding | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 3 | Implement OpenCV face capture and photo storage | Sprint 1 | Sprint 1 | Project Team | Coding | 3- Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 4 | Implement password hashing and login validation | Sprint 1 | Sprint 1 | Project Team | Coding | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 5 | Create exam session on successful login and update logout status | Sprint 1 | Sprint 1 | Project Team | Coding | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 1900-01-05 | Build dashboard for session history and status | Sprint 2 | Sprint 2 | Project Team | Build | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 1900-01-06 | Implement live identity verification using registered photo | Sprint 2 | Sprint 2 | Project Team | Coding | 3- Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 1900-01-07 | Implement exam session state transitions | Sprint 2 | Sprint 2 | Project Team | Coding | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 1900-01-08 | Create question bank model and seed assessment questions | Sprint 3 | Sprint 3 | Project Team | Coding | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 1900-01-09 | Implement randomized question selection and answer persistence | Sprint 3 | Sprint 3 | Project Team | Coding | 3- Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 1900-01-10 | Capture tab switch and focus loss browser events | Sprint 3 | Sprint 3 | Project Team | Coding | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | 1900-01-11 | Implement webcam face and eye status analysis | Sprint 3 | Sprint 3 | Project Team | Coding | 3- Completed | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | 1900-01-12 | Implement tab-switch and focus-loss threshold rules | Sprint 4 | Sprint 4 | Project Team | Coding | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | 1900-01-13 | Implement face absence and multiple-face violation rules | Sprint 4 | Sprint 4 | Project Team | Coding | 3- Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | 1900-01-14 | Implement combined suspicious activity rule | Sprint 4 | Sprint 4 | Project Team | Coding | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | 1900-01-15 | Generate session monitoring report and integrity information | Sprint 4 | Sprint 4 | Project Team | Build | 3- Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | 1900-01-16 | Prepare behaviour features and K-Means clustering workflow | Sprint 4 | Sprint 4 | Project Team | Coding | 3- Completed | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | 1900-01-17 | Execute validation tests for registration and authentication | Sprint 5 | Sprint 5 | Project Team | Testing | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | 1900-01-18 | Execute monitoring threshold and session completion tests | Sprint 5 | Sprint 5 | Project Team | Testing | 3- Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | 1900-01-19 | Review defects, evidence and final submission package | Sprint 5 | Sprint 5 | Project Team | Documentation | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Project scope and architecture needed clarification | Reviewed README, architecture and database models; finalized Sprint 1 scope.
Sprint 1 | Day 3 | OpenCV capture and photo-storage flow required validation | Verified capture route and storage configuration; documented expected registration flow.
Sprint 2 | Day 1 | Identity verification depends on reliable registered photo | Validated registered-photo path and single-face extraction before LBPH comparison.
Sprint 2 | Day 4 | Exam session status transitions needed consistency | Reviewed active session states and standardized login, ready, start and logout transitions.
Sprint 3 | Day 2 | Monitoring events need consistent event names | Aligned browser, webcam and interaction event types with MonitoringEvent model.
Sprint 3 | Day 4 | Webcam detection can return different visual states | Mapped face, no-face, multiple-face and eye-detection states to monitoring events.
Sprint 4 | Day 2 | Threshold values need clear validation scenarios | Used rule-engine configuration thresholds and created boundary test cases.
Sprint 4 | Day 4 | Behaviour clustering requires enough completed sessions | Added a minimum-data check and feature preparation before K-Means execution.
Sprint 5 | Day 2 | Need evidence that core flows work together | Executed registration, duplicate-email, hashing, login/session and monitoring validation scenarios.
Sprint 5 | Day 4 | Final tracker formatting and evidence review | Reviewed Agile, unit-test and defect records for consistency before submission.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 18-Sep-2026 | 20-Sep-2026 | Project Team | Start documenting validation conditions earlier | Stop assuming requirements are self-explanatory | Continue structured code review | Added short review checkpoints for each completed flow.
2 | Sprint 2 | 21-Sep-2026 | 23-Sep-2026 | Project Team | Start checking dependency paths before integration | Stop postponing integration checks | Continue modular implementation | Added integration checks between login, session and verification modules.
3 | Sprint 3 | 24-Sep-2026 | 26-Sep-2026 | Project Team | Start maintaining an event-type reference | Stop using inconsistent event names | Continue incremental testing | Standardized monitoring event names and payload expectations.
4 | Sprint 4 | 27-Sep-2026 | 29-Sep-2026 | Project Team | Start testing threshold boundaries explicitly | Stop validating only normal cases | Continue evidence-based debugging | Added threshold, face-absence, multiple-face and combined-event scenarios.
5 | Sprint 5 | 30-Sep-2026 | 02-Oct-2026 | Project Team | Start final document review earlier | Stop leaving formatting checks to the end | Continue keeping test evidence traceable | Performed final cross-check of project features against Agile and test records.