## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Project Team | 2026-09-18 | Duplicate candidate registration should be rejected for an existing email. | Sprint 1 | Project Team | Logical | Added duplicate-email validation before candidate creation. | 2026-09-18 | Closed | Validated by duplicate-email unit test.
2 | Project Team | 2026-09-18 | Candidate passwords must not be stored in plain text. | Sprint 1 | Project Team | Logical | Implemented Werkzeug password hashing and validation. | 2026-09-18 | Closed | Password hashing test passed.
3 | Project Team | 2026-09-18 | Exam must not start before identity verification succeeds. | Sprint 2 | Project Team | Logical | Restricted exam start to the READY TO START session state. | 2026-09-18 | Closed | Session-state validation added.
4 | Project Team | 2026-09-18 | Monitoring events should be rejected when no active exam session exists. | Sprint 3 | Project Team | Logical | Added active-session checks to monitoring endpoints. | 2026-09-18 | Closed | Invalid-session requests are rejected.
5 | Project Team | 2026-09-18 | Excessive tab switching requires a threshold-based integrity violation. | Sprint 4 | Project Team | Logical | Implemented MAX_TAB_SWITCHES and EXCESSIVE_TAB_SWITCH rule. | 2026-09-18 | Closed | Boundary scenarios validated.
6 | Project Team | 2026-09-18 | Long face absence should receive higher severity than short absence. | Sprint 4 | Project Team | Logical | Implemented separate warning and high-duration face absence thresholds. | 2026-09-18 | Closed | 5-second and 30-second scenarios validated.
7 | Project Team | 2026-09-18 | Combined suspicious behaviours should create a consolidated violation. | Sprint 4 | Project Team | Logical | Added combined tab-switch + focus-loss + face-absence rule. | 2026-09-18 | Closed | Combined-event test passed.
8 | Project Team | 2026-09-18 | K-Means clustering should not run when completed-session data is insufficient. | Sprint 4 | Project Team | Logical | Added minimum three-session check before clustering. | 2026-09-18 | Closed | Safe skip implemented for insufficient data.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others